## Dashboard
Sr. no. | Tags Name | Date to completion | Dev Team Status | Analytics Status | Comments
1 | Product Clicks | 2021-08-15 | Done | Partially pass | Missing CD6,id and Price value populating as string for FREE product
2 | Product Detail Impressions | 2021-08-16 | Done | Partially pass | Missing CD6,id and Price value populating as string for FREE product
3 | Add to cart | 2021-08-10 | Done | Partially pass | Missing CD5,CD6 and variant values.
4 | Remove from cart | 2021-08-09 | Done | Pass
5 | Promotion Click | 2021-08-15 | Done | Partially pass | Creative paramere populating as blank.
6 | Checkout | 2021-08-24 | Done | Fail | Triggering on pageload instead of onClick.
| Product Impression | 2021-08-20 | Done | Partially pass
| Promotion Impression | 2021-08-16 | Done | Partially pass
Remaining:
checkout options
purchases
payment fails

## BugsFixing-test
Sr. No | Tag name | Bugs / Issue | Remark | Status
1 | Add to cart and Remove from cart | While performing QA we found that when adding same item to add to cart it is populating data layer with different array, instead of adding quantity to same array. | Fixed this bug | Done
|  | Same happens with Remove from cart, after removing first item it has one element in remove cart, but after removing another element it keeps adding to it’s array. | Fixed this bug | Done
|  | Maximum 8 quantity should be added for each product but while adding more qty dataLayer is pushing data which should not push if trying to add more than 8 product for any one product | Fixed this bug (this issue was discussed on call with Shreyansh and Ajay) | Done
2 | Product Detail Impression | Observed that while browsing the page if we visit same page by navigating through browsers back button this event gets triggered ‘eeproductView’. | Fixed this bug (this issue was discussed on call with Shreyansh and Ajay) its not bug actually, its working correctly | Done
|  | eeproductView’ event didn’t trigger for this: | Fixed this bug | Done
https://qa.sentosa.com.sg/en/things-to-do/attractions/magical-shores/
|  | Product name is wrong in the page with respect to the attraction page: | This data is correct as per data received by backend only time is displaying half | Done
https://qa.sentosa.com.sg/en/things-to-do/attractions/hydrodash/
3 | ProductClicks | dimension5 is populating as blank for "Magical Shores" | this data is not given in backend so blank value is push | Done
https://qa.sentosa.com.sg/en/things-to-do/attractions/?page=3
| 1. Push price as ‘0’ for ‘free’ – Done |  | Analytics Remark
| 2. Remove ‘$’ from Price and push only number – Done |  | Done
| 3. Checkout step 1 (Datalayer Implementation) – Done |  | Partially done, as some data is populating as NaN.
| 4. Checkout step 2 (Datalayer Implementation) – Done (Guest / registration is pending as there is a issue in login) |  | Partially done, extra parameter is included in actionField ,i.e. action.
| 5. Checkout step 3 (DataLayer Implementation) – Done |  | Partially done, extra parameter is included in actionField ,i.e. action and instead of passtion guest or register , developer is passing both value as given in example
| 6. Payment Fail (DataLayer Implementation) – Done |  | Done
Issue with "eecheckout": As mentioned in the guide there should be two parameter but here one extra action parameter is getting populated.
Issue with "eeproductImpressions" event: -price is populating as NaN
https://qa.sentosa.com.sg/en/things-to-do/attractions/?page=3
Note: | price value paramter is populated as 1 decimal value, it should be 2 decimal value. Example: price is 4.90, and we are getting 4.9. In future price can change like $10.78, then it should populated as 10.78 instead of 10.7

## Bugs 8th August
While performing QA we found that when adding same item to add to cart it is populating data layer with different array, instead of adding quantity to same array.
Same happens with Remove from cart, after removing first item it has one element in remove cart, but after removing another element it keeps adding to it’s array.
For reference see the below screenshot.
Note:- Always clear the Array /Existing product while passing Add to cart or remove items to cart event, before passing new products
Regards,
Ajay

## Product detail impression
Found 3 issue with event "eeproductView" 1. dimension6 is no populating for any product. 2. id value is populating as blank. 3. Product which are free , value for price is populating as "FREE".
Observed that while browsing the page if we visit same page by navigating through browsers back button this event gets triggered 'eeproductView'.
Page not found: https://qa.sentosa.com.sg/en/things-to-do/attractions/animal-encounters/ https://qa.sentosa.com.sg/en/things-to-do/attractions/crane-dance/ https://qa.sentosa.com.sg/en/things-to-do/attractions/kidzania-singapore/ https://qa.sentosa.com.sg/en/things-to-do/attractions/the-maritime-experiential-museum/
eeproductView' event didn't trigger for this: https://qa.sentosa.com.sg/en/things-to-do/attractions/magical-shores/
Product name is wrong in the page with respect to the attraction page: https://qa.sentosa.com.sg/en/things-to-do/attractions/hydrodash/

## Add-Remove from Cart
Found 4 issues with event "eeremoveFromCart" 1. dimension6 is populating as blank for every product 2. dimension5 is populating as blank for every product 3. category is populating as blank for every product 4. variant is blank for every product
Note: Some of the products are not added in the cart. https://qa.sentosa.com.sg/en/things-to-do/attractions/aj-hackett-sentosa/

## ProductClicks
Found 4 issues with event "eeproductClick": 1. category is populating as blank for every product 2. dimension6 is populating as blank for every product 3. id is populating as blank for every product 4. Product which are free, value for price is populating as "FREE".
dimension5 is populating as blank for "Magical Shores" https://qa.sentosa.com.sg/en/things-to-do/attractions/?page=3

## PromotionClicks
Found issue with event "eepromotionClicks": 1. creative is populating as blank for every promo and offers. 2. position should not populate as string type, it should be an int
PROMOS and OFFERS not found: https://qa.sentosa.com.sg/en/deals/promos/ - ATTRACTIONS - PLACES TO STAY

## Checkout
This event is triggering on Pageload of 'Order Summary' page, instead of on click of 'Checkout' button.
Missing parameter : dimension5, dimension6

## Product Impressions
Observation found with event "eeproductImpressions" 1. dimension6 is populating as blank 2. id value is populating as blank. 3. category value is populating as blank. 4. Price value is containing $ symbol 5. Price also populating as Free 6. Also noticed, position parameter is reseting value after clicking on load more option
list parameter are not passed as pipe ( ¦ )
list is populated as without pipe ( ¦ )

## Promotion Impressions
Issues with "eepromotionImpression": - position is populated as string type. //It should be an integer - "PROMOS FOUND" is same for all the tab such as: ATTRACTIONS, PLACES TO STAY, DINING - "Filter By" button is not working. Like if you select any one or two filter and click on APPLY, it's not showing proper output. - creative is populated as "Promos" for every PROMOs. It should be dynamic.
filters are working on this page only: https://qa.sentosa.com.sg/en/deals/promos?page=2
filter are not working on this page: https://qa.sentosa.com.sg/en/deals/promos
when I click on Mastercard filter, creative is populated as "promo" which is wrong. It should be "Mastercard". Total number of PROMOS are 10 but here in position is populated as "13"
In every filter option only this PROMO is coming. Filter is not working for all this PROMOs